## Foglio1
In this excel file you can find the used roadmap during the development. Ongoing known ugs are listed, future small ideas and future plans/task of development are also included.
| 0.1 Version - prototyping | [11 empty] | 0.2 First playable version | [5 empty] | 0.3 Improved version |  |  |  | 0.4 Optimized and tweaked version (Delivery of UNI assignment) | [5 empty] | 0.5 Future Version prototype
Version: |  | 0.1.0 |  | 0.1.1 |  | 0.1.2 |  | 0.1.3 |  | 0.1.4 |  | 0.1.5 |  | 0.2.0 |  | 0.2.1 |  | 0.2.3 |  | 0.3.0 |  | 0.3.1 |  | 0.4.0 |  | 0.4.1 |  | 0.4.2 |  | 0.5.0
| ✓ | Basic Player Control | ✓ | Basic AI Follow Logic | ✓ | Basic Main Menu | ✓ | Search for mesh assets | ✓ | Player model | ✓ | Complete Bug Fixing and Heavy AI Testing | ✓ | AI status icons event handlerer | ✓ | Controls refinement | ✓ | First Level (1st iteration) | ✓ | Audio system | ✓ | Options menu | ✓ | Camera tweaks (render and visually) | ✓ | Levels 1-2 design tweaking | ✓ | Final day tweaks |  | Complete game re-design (gameplay, logic, mechanics, etc.)
| ✓ | Basic Player Animations | ✓ | Basic AI Patrol Logic | ✓ | Basic UI | ✓ | Organize assets + code refactoring | ✓ | Enemy model(s) | ✓ | Complete Main Menu | ✓ | Win and Game Over UI | ✓ | Player/AI animations/logic refinement | ✓ | Second Level (1st iteration) | ✓ | Stamina System | ✓ | Resolutions Manage | ✓ | Graphics optimization + presets on menu | ✓ | Level heavy testing |  |  |  | Restart project from scratch
| ✓ | Basic World Props etc. | ✓ | Basic Game Win Logic | ✓ | Input refinement + PAD mapping | ✓ | 3D visual text clues for tutorial |  |  | ✓ | Complete in-game menu | ✓ | Remaining objects to steal indicator UI | ✓ | AI parameters refinement | ✓ | Tutorial Scene tweaking | ✓ | Rain System on 2nd level |  |  | ✓ | AI logic tweaking and optimization | ✓ | Test on low end machine |  |  |  | Choose target platform and game genre
[7 empty] | ✓ | Tutorial scene (1st iteration) |  |  | ✓ | PlayGround/Test AI level | ✓ | Maps border |  |  | ✓ | Tresure prop object |  |  |  |  | ✓ | Stealing UI | ✓ | User (friends) user testing |  |  |  | Planning of development
[25 empty] | ✓ | Tuorial level final tweaks |  |  |  | Tools for level design
Assets for variety and complex tools
Complete Pad Support
To Fix: |  | Player glitch inside objects very easily. The cause is the player movement system. It acts on chaning player absolute transform.position. Player is not moved by phyisics, but every update() call it teleports, so it goes inside or over objects. The fix is in reworking the movement system! |  |  |  | Not implemented Ideas: | Transparent grass when hiding on it |  |  | TODO Tomorrow:
Press key to steal indicator UI
More controllable debug flags for paths
Can't win if followed? Or yes?
Visual effect while hiding
Optimized trigger colliders (for example, sound clue collider only colliding with player layer - less performance impact)
Menu support for pad!
Advanced patrol paths build tool
Spotted on ai collision
Grass and stuff animation (level feels static)
User Testing
User 1: v0.4.0 (Daniele - Master degree IT student, plays a lot of videogames)
| IMPLEMENTED | Wants pad support (at least in game)
| TODO | Wants better feedback while stealing objects (progress bar and not text)
| IMPROVED | BUG: it is easy to glitch outside maps border
| FIXED | BUG: ambient sound glitched on tutorial level
| IMPROVED | BUG: guards can easily lost your track if you run around them in a fast and zigzag fashion
User 2: v0.4.1 (after user 1 tweaks) (Stefano - Mechanical designer, plays video games occasionally)
| IMPROVED | BUG: too easy to glitch outside map borders | [5 empty] | LOL:
| IMPROVED | Guards are too fast | [5 empty] | https://www.youtube.com/watch?v=1HKQBnlvnaQ
| TODO | Wants a minimap (or at least he wants to see the map at the beginning of the level)
| FIXED | BUG: He has a 21:9 monitor, main menu is broken
| TODO | He wants sounds clue when guards spot you. He also wants more sounds in general
User 3: v0.4.1 (after user 1 tweaks) (Federico - Bachelor's degr. student in IT UNIUD, plays some videogames)
| IMPROVED | Guards are too fast
| IMPROVED | He thinks there should be more covers in some map areas